## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW Priority | Dependency | Assignee | Status
S1 | S1 | US-01 | Understand the overall project objective and system architecture so that the dashboard aligns with the end-to-end platform vision. | MUST HAVE | None | Samruddhi | 3-Completed
S1 | S1 | US-02 | Learn basic stock market concepts such as OHLC data, indicators, and trading flow to correctly interpret dashboard metrics. | SHOULD HAVE | None | Samruddhi | 3-Completed
S1 | S1 | US-03 | Learn basic stock market concepts such as OHLC data, indicators, and trading flow to correctly interpret dashboard metrics. | MUST HAVE | None | Samruddhi | 3-Completed
S2 | S2 | US-04 | Learn supporting tools such as Figma, Streamlit components, charts, ML basics, and backtesting concepts for dashboard development readiness. | SHOULD HAVE | None | Samruddhi | 3-Completed
S2 | S2 | US-05 | Analyze dashboard requirements to identify required pages, metrics, charts, and user interactions. | MUST HAVE | US-01, US-04 | Samruddhi | 3-Completed
S2 | S2 | US-06 | Evaluate different dashboard frameworks and finalize Streamlit as the primary visualization framework. | MUST HAVE | US-05 | Samruddhi | 3-Completed
S3 | S3 | US-07 | Design dashboard wireframes and UI blueprints using Figma to define layout and navigation flow. | MUST HAVE | US-06 | Samruddhi | 3-Completed
S3 | S3 | US-08 | Build initial Streamlit dashboard structure with multi-page navigation. | MUST HAVE | US-07 | Samruddhi | 3-Completed
S4 | S4 | US-09 | Implement market data visualization including candlestick charts, volume bars, and price summary cards. | MUST HAVE | US-08 | Samruddhi | 3-Completed
S4 | S4 | US-10 | Integrate technical indicators such as RSI, MACD, and trend signals into the dashboard. | MUST HAVE | US-09 | Samruddhi | 3-Completed
S5 | S5 | US-11 | Integrate ML outputs including BUY/SELL/HOLD signals and confidence scores into the dashboard UI. | MUST HAVE | ML Team | Samruddhi | 3-Completed
S5 | S5 | US-12 | Integrate backtesting outputs such as equity curves, performance metrics, and trade statistics. | MUST HAVE | Backtesting Team | Samruddhi | 3-Completed
S6 | S6 | US-13 | Integrate alert and notification visualization so users can monitor important trading events. | MUST HAVE | Alerts Team | Samruddhi | 3-Completed
S6 | S6 | US-14 | Improve dashboard usability, layout consistency, and visual clarity based on team feedback. | SHOULD HAVE | US-13 | Samruddhi | 3-Completed
S7 | S7 | US-15 | Validate dashboard data against backend APIs to ensure correctness and reliability. | MUST HAVE | US-11, US-12 | Samruddhi | 3-Completed
S7 | S7 | US-16 | Handle API failures gracefully and display fallback messages in the dashboard. | SHOULD HAVE | US-15 | Samruddhi | 3-Completed
S8 | S8 | US-17 | Prepare demo video showcasing dashboard features, integrations, charts, and alerts. | SHOULD HAVE | None | Samruddhi | 3-Completed
S8 | S8 | US-18 | Create detailed documentation explaining dashboard pages, visualizations, and integrations. | SHOULD HAVE | US-17 | Samruddhi | 3-Completed
S8 | S8 | US-19 | Review and finalize Dashboard & Visualization Hub for final internship submission. | MUST HAVE | US-18 | Samruddhi | 3-Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2
[8 empty] | 95 | 46 | 49
SPRINT 1 BACKLOG – Dashboard & Visualization Hub
US-01 | T1.1 | Understand project scope and dashboard responsibility | Day 1 | Day 1 | Samruddhi | Learning | Done | 4 | 4 | 0
US-02 | T1.2 | Study stock market basics, indicators, and signal flow | Day 1 | Day 2 | Samruddhi | Learning | Done | 6 | 3 | 3
US-03 | T1.3 | Review existing dashboards and trading platforms | Day 2 | Day 2 | Samruddhi | Research | Done | 5 | 2 | 3
SPRINT 2 BACKLOG – UI Planning & Tool Finalization
US-04 | T2.1 | Explore Streamlit features for dashboard development | Day 1 | Day 2 | Samruddhi | Research | Done | 5 | 2 | 3
US-05 | T2.2 | Analyze dashboard requirements from ML & backtesting teams | Day 2 | Day 3 | Samruddhi | Analysis | Done | 6 | 3 | 3
SPRINT 3 BACKLOG – Dashboard Wireframes & Structure
US-06 | T3.1 | Create dashboard wireframes in Figma | Day 1 | Day 2 | Samruddhi | Analysis | Done | 6 | 3 | 3
US-07 | T3.2 | Finalize dashboard page flow and navigation | Day 2 | Day 3 | Samruddhi | Development | Done | 5 | 2 | 3
SPRINT 4 BACKLOG – Core Dashboard Development
US-08 | T4.1 | Build overview page with system summary & navigation | Day 1 | Day 2 | Samruddhi | Development | Done | 6 | 3 | 3
US-09 | T4.2 | Implement stock price charts and market snapshot | Day 2 | Day 3 | Samruddhi | Development | Done | 7 | 3 | 4
SPRINT 4 BACKLOG – Core Dashboard Development
US-08 | T4.1 | Build overview page with system summary & navigation | Day 1 | Day 2 | Samruddhi | Development | Done | 6 | 3 | 3
US-09 | T4.2 | Implement stock price charts and market snapshot | Day 2 | Day 3 | Samruddhi | Development | Done | 7 | 3 | 4
SPRINT 5 BACKLOG – ML & Backtesting Integration
US-10 | T5.1 | Integrate ML signals and confidence levels | Day 1 | Day 3 | Samruddhi | Development | Done | 8 | 4 | 4
US-11 | T5.2 | Display backtesting metrics and equity curves | Day 2 | Day 4 | Samruddhi | Development | Done | 7 | 3 | 4
SPRINT 6 BACKLOG – Alerts, Export & Polish
US-12 | T6.1 | Integrate alerts UI and alert status display | Day 1 | Day 2 | Samruddhi | Development | Done | 6 | 3 | 3
US-13 | T6.2 | Add export options and final UI improvements | Day 2 | Day 3 | Samruddhi | Testing | Done | 5 | 2 | 3
US-14 | T6.3 | Prepare demo video, PPT, and documentation | Day 3 | Day 4 | Samruddhi | Review | Done | 6 | 3 | 3

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Initial lack of clarity on overall AI Stock Signal project scope and expected outputs | Discussed project objectives with mentor and reviewed reference materials
Sprint 1 | Day 4 | Confusion about role-specific responsibilities between Dashboard, ML, and Backtesting teams | Conducted cross-team discussion to clearly define inputs and outputs
Sprint 2 | Day 6 | Difficulty understanding Agile story writing and MOSCOW prioritization | Reviewed Agile template and clarified doubts during mentor-led session
Sprint 2 | Day 8 | Uncertainty in designing dashboard workflow before final ML outputs | Created a flexible dashboard wireframe that supports dynamic ML data
Sprint 3 | Day 11 | Issues in setting up Streamlit environment and library compatibility | Reinstalled dependencies and validated setup using sample applications
Sprint 3 | Day 13 | Challenges in rendering interactive charts with stock data | Referred official documentation and tested multiple visualization libraries
Sprint 4 | Day 16 | Delay in receiving finalized data format from Backtesting team | Used mock JSON data to continue dashboard development
Sprint 5 | Day 22 | Difficulty integrating ML Buy/Hold/Sell signals with confidence scores | Coordinated with ML team to standardize signal output structure
Sprint 6 | Day 27 | Performance issues when loading multiple dashboard components | Optimized data loading and applied caching techniques in Streamlit
Sprint 7 | Day 31 | Uncertainty around alert trigger conditions and notification flow | Designed configurable alert logic and validated with mentor feedback
Sprint 7 | Day 31 | Uncertainty around alert trigger conditions and notification flow | Designed configurable alert logic and validated with mentor feedback

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-26 | 2025-12-02 | Samruddhi ,Polipalli Sai,Tarun,Shamrutha | Reviewing project documentation and understanding stock market basics | Assuming requirements without clarification | Participating in mentor and team discussions | Conducted requirement clarification session and aligned on project scope
2 | Sprint 2 | 2025-12-03 | 2025-12-09 | Samruddhi ,Polipalli Sai,Tarun,Shamrutha | Structuring Agile stories and sprint timelines | Writing vague or task-level stories | Following Agile methodology consistently | Refined user stories using MOSCOW prioritization
3 | Sprint 3 | 2025-12-10 | 2025-12-16 | Tarun,Polipalli Sai,Samruddhi Junavane,Shamrutha | Setting up Streamlit dashboard and Python environment | Delaying UI testing | Practicing incremental coding and testing | Successfully completed environment setup and basic dashboard layout
4 | Sprint 4 | 2025-12-17 | 2025-12-23 | Tarun,Samruddhi Junavane,Shamrutha | Integrating sample stock data and visualizations | Waiting for finalized ML outputs | Coordinating with ML and backtesting teams | Used mock data to complete dashboard visual components
5 | Sprint 5 | 2025-12-24 | 2025-12-30 | Tarun, Samruddhi ,Shamrutha | Integrating ML Buy/Sell signals into dashboard | Hardcoding values in UI | Using dynamic and configurable data pipelines | Standardized ML signal format and integrated it into the dashboard
6 | Sprint 6 | 2025-12-31 | 2026-01-06 | Tarun,Shamrutha | Integrating alert functionality and trading notifications into the dashboard | Pushing changes without cross-team confirmation | Incremental testing after every integration | Resolved integration inconsistencies and stabilized dashboard features
7 | Sprint 7 | 2026-01-07 | 2026-01-13 | Tarun,Samruddhi,Shamrutha | Validating end-to-end data flow across all dashboard features | Ignoring minor UI inconsistencies | Peer reviews and team feedback sessions | Finalized feature set and prepared the system for demo and documentation
8 | Sprint 8 | 2026-01-14 | 2026-01-28 | Shamrutha,Samruddhi,Pollipalli Sai | Demo Video,Documentation,PPT | Leaving presentation and docs to last minute | Team collaboration | Completed PPT, demo video, final documentation, and project submission